# IMPLEMENTATION PLAN

## Digital Agritech Platform – Limpopo, South Africa

Project: AFAP Digital Agritech Platform & Value Chain Integration
Client: African Fertilizer and Agribusiness Partnership (AFAP)
Document Version: 1.0
Date: [Insert Date]
Status: Draft for Review

## 1. Executive Summary

This Implementation Plan outlines the phased delivery approach, detailed work breakdown, resource allocation, timelines, and success criteria for the AFAP Digital Agritech Platform. The plan covers the full 36-month contract period, broken into 5 distinct phases, with clear milestones, deliverables, and dependencies at each stage.

The plan is designed to:

- De-risk delivery through an early pilot phase with a defined checkpoint

- Maximize user adoption through structured training and community engagement

- Ensure technical quality through continuous testing, monitoring, and iteration

- Deliver measurable value to AFAP, farmers, and ecosystem partners

## 2. Implementation Phases Overview

| Phase | Timeline | Duration | Key Objective |
| --- | --- | --- | --- |
| Phase 1: Mobilisation & Foundation | Months 1–3 | 3 months | Establish team, tools, infrastructure; finalise requirements; build core platform foundation |
| Phase 2: Pilot Implementation | Months 4–9 | 6 months | Deploy working platform to pilot cohort; validate with real users; iterate based on feedback |
| Phase 3: Scale-Up | Months 10–18 | 9 months | Expand to full Limpopo rollout; integrate all modules; onboard all user segments |
| Phase 4: Optimisation | Months 19–24 | 6 months | Refine ML models; performance tuning; feature enhancements; mid-term review |
| Phase 5: Maintenance & Support | Months 25–36 | 12 months | Steady-state operations; SLA-based support; upgrades; transition planning |

## 3. Phase 1: Mobilisation & Foundation (Months 1–3)

### 3.1 Objectives

- Establish project governance and team

- Set up development, testing, and production environments

- Finalise detailed requirements with AFAP

- Build core platform foundation (auth, farmer registration, USSD/SMS)

- Establish data protection and security framework

### 3.2 Detailed Work Breakdown

| # | Task | Duration | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 1.1 | Project kickoff with AFAP | Week 1 | Project Director | - |
| 1.2 | Finalise team staffing and roles | Week 1–2 | Project Director | - |
| 1.3 | Set up development environment (GitHub, CI/CD, cloud) | Week 1–2 | DevOps Engineer | - |
| 1.4 | Requirements validation workshops with AFAP | Week 2–4 | Solutions Architect | 1.1 |
| 1.5 | Finalise system architecture and tech stack | Week 3–4 | Solutions Architect | 1.4 |
| 1.6 | Set up Supabase project; initial schema design | Week 3–4 | Backend Engineers | 1.5 |
| 1.7 | Develop core auth module (registration, login, roles) | Week 4–6 | Backend Engineers | 1.6 |
| 1.8 | Develop farmer registration module (basic) | Week 5–7 | Backend Engineers | 1.7 |
| 1.9 | Develop USSD/SMS gateway integration (basic menu) | Week 5–8 | USSD Specialist | 1.6 |
| 1.10 | Develop basic web admin dashboard | Week 6–9 | Frontend Engineers | 1.7 |
| 1.11 | Develop React Native boilerplate; offline-first setup | Week 6–9 | Mobile Engineers | 1.7 |
| 1.12 | Document data protection and security framework | Week 7–10 | QA & DevOps | 1.5 |
| 1.13 | Unit testing setup and initial test coverage | Week 8–10 | QA & DevOps | 1.8 |
| 1.14 | Phase 1 internal review and sign-off | Week 11–12 | Project Director | 1.8–1.13 |

### 3.3 Phase 1 Deliverables

| Deliverable | Format | Recipient |
| --- | --- | --- |
| Project kickoff report | PDF | AFAP PM |
| Requirements validation document | Word/PDF | AFAP PM |
| System architecture document | Word/PDF | AFAP PM |
| Data protection and security framework | Word/PDF | AFAP PM |
| Working MVP: Farmer registration (web + mobile + USSD) | Live demo | AFAP PM |
| CI/CD pipeline operational | Access link | AFAP PM |
| Phase 1 review report | PDF | AFAP PM |

### 3.4 Phase 1 Resource Allocation

| Role | Effort (Person-Months) |
| --- | --- |
| Project Director | 0.3 |
| Solutions Architect | 0.5 |
| Backend Engineers (2) | 1.5 |
| Frontend Engineers (2) | 1.0 |
| Mobile Engineers (2) | 1.0 |
| USSD Specialist | 0.5 |
| QA & DevOps Engineer | 0.5 |
| Training Lead | 0.2 |
| Total | 5.5 person-months |

## 4. Phase 2: Pilot Implementation (Months 4–9)

### 4.1 Objectives

- Deploy platform to a defined pilot cohort (farmers, CBAs, agrodealers)

- Validate core functionality with real users

- Collect feedback and iterate

- Establish initial ecosystem partnerships (financial institutions, off-takers)

- Begin user training and adoption activities

### 4.2 Pilot Cohort Definition

| Cohort Segment | Target Count | Selection Criteria |
| --- | --- | --- |
| Farmers | 500–1,000 | Diverse crops; different literacy levels; across Limpopo districts |
| CBAs | 20–30 | Active extension agents; geographic spread |
| Agrodealers | 10–15 | Different sizes; diverse locations |
| Financial Institutions | 2–3 | Willing to integrate with pilot |
| Off-takers/Buyers | 2–3 | Active in Limpopo |

### 4.3 Detailed Work Breakdown

| # | Task | Duration | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 2.1 | Define pilot cohort with AFAP | Week 13–14 | Project Director | 1.14 |
| 2.2 | Complete farmer registration module (full features) | Week 13–16 | Backend Engineers | 1.8 |
| 2.3 | Complete mobile app (registration + input ordering) | Week 13–17 | Mobile Engineers | 1.11 |
| 2.4 | Complete USSD menu (registration + basic advisory) | Week 14–17 | USSD Specialist | 1.9 |
| 2.5 | Develop advisory module (rules-based) | Week 15–18 | Backend Engineers + Data Scientist | 2.2 |
| 2.6 | Develop input supply module (basic ordering) | Week 16–20 | Backend Engineers | 2.2 |
| 2.7 | Integrate first financial institution API (sandbox) | Week 17–21 | Backend Engineers | 2.2 |
| 2.8 | Develop admin dashboard (basic M&E) | Week 16–20 | Frontend Engineers | 2.2 |
| 2.9 | Onboard pilot users (training workshops) | Week 18–22 | Training Lead | 2.1, 2.3 |
| 2.10 | Pilot launch (go-live with cohort) | Week 22 | Project Director | 2.3–2.9 |
| 2.11 | User feedback collection (surveys, interviews) | Week 22–26 | Training Lead | 2.10 |
| 2.12 | Iterative fixes and enhancements | Week 22–30 | All Engineers | 2.11 |
| 2.13 | Mid-pilot review with AFAP | Week 30 | Project Director | 2.12 |
| 2.14 | Phase 2 review and pilot report | Week 32–36 | Project Director | 2.13 |

### 4.4 Phase 2 Deliverables

| Deliverable | Format | Recipient |
| --- | --- | --- |
| Pilot cohort definition | Word/PDF | AFAP PM |
| Fully functional platform (pilot release) | Live platform | AFAP PM |
| USSD and SMS operational | Live service | Farmers, CBAs |
| Mobile app in app store (or APK distribution) | APK/Play Store | Farmers, CBAs |
| Training materials and workshops delivered | PPT + manuals | AFAP PM |
| Pilot feedback report | Word/PDF | AFAP PM |
| Integration with 2+ financial institutions (sandbox) | API live | AFAP PM |
| Phase 2 review report | PDF | AFAP PM |

### 4.5 Phase 2 Resource Allocation

| Role | Effort (Person-Months) |
| --- | --- |
| Project Director | 1.0 |
| Solutions Architect | 1.5 |
| Backend Engineers (2) | 4.0 |
| Frontend Engineers (2) | 3.0 |
| Mobile Engineers (2) | 4.0 |
| USSD Specialist | 2.0 |
| Data Scientist / ML Engineer | 1.5 |
| QA & DevOps Engineer | 2.0 |
| Training Lead | 2.0 |
| Agronomy Advisor | 1.0 |
| Total | 22.0 person-months |

### 4.6 Pilot Success Criteria (Checkpoint)

To proceed to Phase 3, the pilot must meet:

| Metric | Target |
| --- | --- |
| User satisfaction (survey) | ≥ 75% satisfied/very satisfied |
| Platform stability (crash rate) | < 2% |
| USSD/SMS uptime | ≥ 99% |
| Transactions processed | ≥ 1,000 cumulative |
| Feedback actioned | ≥ 80% of critical feedback addressed |

## 5. Phase 3: Scale-Up (Months 10–18)

### 5.1 Objectives

- Expand farmer, CBA, and agrodealer onboarding across Limpopo

- Launch full module suite (aggregation, financial services, traceability)

- Complete all third-party integrations

- Implement ML advisory model enhancements

- Establish full M&E and reporting framework

### 5.2 Detailed Work Breakdown

| # | Task | Duration | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 3.1 | Scale-up planning with AFAP | Week 37–40 | Project Director | 2.14 |
| 3.2 | Develop commodity aggregation module | Week 37–44 | Backend Engineers | 2.6 |
| 3.3 | Develop traceability module | Week 39–46 | Backend Engineers | 3.2 |
| 3.4 | Complete financial services module (credit, insurance, e-vouchers) | Week 41–50 | Backend Engineers | 2.7 |
| 3.5 | Integrate full financial institution APIs (production) | Week 45–52 | Backend Engineers | 3.4 |
| 3.6 | Integrate off-taker/buyer APIs | Week 43–48 | Backend Engineers | 3.2 |
| 3.7 | Complete mobile app (all modules) | Week 40–50 | Mobile Engineers | 3.2, 3.3, 3.4 |
| 3.8 | Complete USSD menu (all modules) | Week 41–48 | USSD Specialist | 3.2, 3.3 |
| 3.9 | Train ML advisory model with pilot data | Week 42–50 | Data Scientist | 2.5 |
| 3.10 | Develop full M&E dashboards | Week 44–52 | Frontend Engineers | 3.2, 3.3 |
| 3.11 | Automated reporting engine | Week 48–54 | Backend Engineers | 3.10 |
| 3.12 | Scale-up training (train-the-trainer) | Week 50–60 | Training Lead | 3.1 |
| 3.13 | Phased farmer onboarding (wave 1: 5,000 farmers) | Week 52–62 | Training Lead + CBAs | 3.12 |
| 3.14 | Phased farmer onboarding (wave 2: 10,000 farmers) | Week 58–68 | Training Lead + CBAs | 3.13 |
| 3.15 | Full ecosystem partner onboarding | Week 54–64 | Project Director | 3.5, 3.6 |
| 3.16 | Phase 3 review and scale-up report | Week 70–72 | Project Director | 3.14 |

### 5.3 Phase 3 Deliverables

| Deliverable | Format | Recipient |
| --- | --- | --- |
| Full platform (all 7 ToR modules) | Live platform | AFAP PM |
| Mobile app full release | Play Store | All users |
| USSD full menu | Live USSD | Farmers |
| Financial services integration (production) | Live APIs | AFAP + FIs |
| ML advisory model (trained) | Integrated | Farmers |
| M&E dashboards (real-time) | Live | AFAP PM |
| Automated donor reports | Scheduled PDF | AFAP PM |
| Training program complete | Report + sign-off | AFAP PM |
| Onboarding of 15,000+ farmers | Database records | AFAP PM |
| Phase 3 review report | PDF | AFAP PM |

### 5.4 Phase 3 Resource Allocation

| Role | Effort (Person-Months) |
| --- | --- |
| Project Director | 2.0 |
| Solutions Architect | 3.0 |
| Backend Engineers (3) | 12.0 |
| Frontend Engineers (2) | 6.0 |
| Mobile Engineers (2) | 6.0 |
| USSD Specialist | 2.0 |
| Data Scientist / ML Engineer | 3.0 |
| QA & DevOps Engineer | 4.0 |
| Training Lead | 4.0 |
| Agronomy Advisor | 2.0 |
| Total | 44.0 person-months |

### 5.5 Scale-Up Success Metrics

| Metric | End of Phase 3 Target |
| --- | --- |
| Farmers registered | ≥ 15,000 |
| Farmers active (≥1 transaction/month) | ≥ 70% |
| Agrodealers onboarded | ≥ 50 |
| CBAs onboarded | ≥ 100 |
| Financial institutions integrated | ≥ 5 |
| Off-takers integrated | ≥ 5 |
| Credit applications processed | ≥ 500 |
| Platform uptime | ≥ 99.5% |

## 6. Phase 4: Optimisation (Months 19–24)

### 6.1 Objectives

- Refine ML advisory model with accumulated data

- Performance tuning and scalability testing

- Feature enhancements based on user feedback

- Conduct mid-term security audit

- Expand ecosystem partnerships

- Prepare for post-contract sustainability

### 6.2 Detailed Work Breakdown

| # | Task | Duration | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 4.1 | ML advisory model refinement (iteration 2) | Month 19–21 | Data Scientist | 3.9 |
| 4.2 | Credit scoring model refinement | Month 19–22 | Data Scientist | 3.4 |
| 4.3 | Performance load testing and optimisation | Month 20–22 | QA & DevOps | 3.16 |
| 4.4 | Security audit and penetration testing | Month 21–23 | QA & DevOps | 1.12 |
| 4.5 | Feature enhancement backlog (based on feedback) | Month 20–24 | All Engineers | 3.16 |
| 4.6 | Expanded partner integrations | Month 21–24 | Backend Engineers | 3.15 |
| 4.7 | User feedback analysis and UX improvements | Month 20–24 | Frontend + Mobile Engineers | 3.16 |
| 4.8 | Mid-term review with AFAP | Month 23 | Project Director | 4.1–4.7 |
| 4.9 | Phase 4 review and optimisation report | Month 24 | Project Director | 4.8 |

### 6.3 Phase 4 Deliverables

| Deliverable | Format | Recipient |
| --- | --- | --- |
| Refined ML advisory model | Integrated | Farmers |
| Refined credit scoring model | Integrated | FIs |
| Performance test report | PDF | AFAP PM |
| Security audit report | PDF | AFAP PM |
| Feature enhancement release | Live platform | All users |
| Mid-term review report | PDF | AFAP PM |
| Optimisation plan for Phase 5 | PDF | AFAP PM |

### 6.4 Phase 4 Resource Allocation

| Role | Effort (Person-Months) |
| --- | --- |
| Project Director | 1.5 |
| Solutions Architect | 2.0 |
| Backend Engineers (2) | 6.0 |
| Frontend Engineers (1) | 3.0 |
| Mobile Engineers (1) | 3.0 |
| Data Scientist / ML Engineer | 3.0 |
| QA & DevOps Engineer | 3.0 |
| Training Lead | 1.0 |
| Total | 22.5 person-months |

## 7. Phase 5: Maintenance & Support (Months 25–36)

### 7.1 Objectives

- Steady-state operations with SLA-based support

- Scheduled platform upgrades and maintenance

- Ongoing user training and adoption support

- Transition planning for post-contract sustainability

- Continuous ecosystem partner onboarding

### 7.2 Detailed Work Breakdown

| # | Task | Duration | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 5.1 | Transition to steady-state operations | Month 25–26 | Project Director | 4.9 |
| 5.2 | SLA-based technical support (ticketing) | Month 25–36 | All Engineers | 5.1 |
| 5.3 | Scheduled maintenance (monthly) | Month 25–36 | QA & DevOps | 5.1 |
| 5.4 | Quarterly platform upgrades | Quarter 1–4 | All Engineers | 5.1 |
| 5.5 | Ongoing training and refresher workshops | Month 25–36 | Training Lead | 5.1 |
| 5.6 | Ecosystem partner expansion (new FIs, off-takers) | Month 25–34 | Project Director | 4.6 |
| 5.7 | Continuous user feedback and improvement | Month 25–36 | All Engineers | 5.1 |
| 5.8 | Quarterly performance reporting to AFAP | Month 27, 30, 33, 36 | Project Director | 5.1 |
| 5.9 | Transition planning for post-contract | Month 33–36 | Project Director | 5.1 |
| 5.10 | Final project report and handover | Month 36 | Project Director | 5.9 |

### 7.3 Phase 5 Deliverables

| Deliverable | Format | Recipient |
| --- | --- | --- |
| SLA framework and support process | Document | AFAP PM |
| Quarterly performance reports | PDF | AFAP PM |
| Quarterly upgrade releases | Live platform | All users |
| Training completion reports | PDF | AFAP PM |
| Transition plan | PDF | AFAP PM |
| Final project report | PDF | AFAP PM |
| Complete platform handover (code, docs, infrastructure) | Access + documents | AFAP PM |

### 7.4 Phase 5 Resource Allocation

| Role | Effort (Person-Months) |
| --- | --- |
| Project Director | 3.0 |
| Solutions Architect | 2.0 |
| Backend Engineers (1) | 6.0 |
| Frontend Engineers (1) | 4.0 |
| Mobile Engineers (1) | 4.0 |
| Data Scientist / ML Engineer | 2.0 |
| QA & DevOps Engineer | 3.0 |
| Training Lead | 2.0 |
| Total | 26.0 person-months |

## 8. Total Resource Summary

### 8.1 Resource Allocation by Phase

| Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Project Director | 0.3 | 1.0 | 2.0 | 1.5 | 3.0 | 7.8 |
| Solutions Architect | 0.5 | 1.5 | 3.0 | 2.0 | 2.0 | 9.0 |
| Backend Engineers | 1.5 | 4.0 | 12.0 | 6.0 | 6.0 | 29.5 |
| Frontend Engineers | 1.0 | 3.0 | 6.0 | 3.0 | 4.0 | 17.0 |
| Mobile Engineers | 1.0 | 4.0 | 6.0 | 3.0 | 4.0 | 18.0 |
| USSD Specialist | 0.5 | 2.0 | 2.0 | - | - | 4.5 |
| Data Scientist / ML Engineer | - | 1.5 | 3.0 | 3.0 | 2.0 | 9.5 |
| QA & DevOps Engineer | 0.5 | 2.0 | 4.0 | 3.0 | 3.0 | 12.5 |
| Training Lead | 0.2 | 2.0 | 4.0 | 1.0 | 2.0 | 9.2 |
| Agronomy Advisor | - | 1.0 | 2.0 | - | - | 3.0 |
| Total Person-Months | 5.5 | 22.0 | 44.0 | 22.5 | 26.0 | 120.0 |

### 8.2 Team Composition by Phase

| Phase | Core Team Size | Description |
| --- | --- | --- |
| Phase 1 | 8–10 | Full team minus specialists (Agronomy Advisor) |
| Phase 2 | 12–14 | Full team plus Data Scientist and Agronomy Advisor |
| Phase 3 | 14–16 | Full team expanded (additional backend) |
| Phase 4 | 10–12 | Core team reduced (part-time specialists) |
| Phase 5 | 8–10 | Core maintenance team |

## 9. Critical Dependencies & Risk Mitigation

### 9.1 Key Dependencies

| Dependency | Owner | Timeline | Fallback Plan |
| --- | --- | --- | --- |
| AFAP requirements sign-off | AFAP PM | Month 1–2 | Use draft ToR as baseline; iterative refinement |
| Financial institution API access | Partner FIs | Month 4–6 | Build mock APIs for development; sandbox integration |
| Telecom USSD/SMS gateway access | Africa's Talking | Month 3–4 | Alternative providers (Clickatell, Vodacom) |
| Farmer pilot cohort availability | AFAP PM | Month 4 | Use alternative CBAs/communities |
| Off-taker interest/agreement | AFAP PM + Partner | Month 8–10 | Delay market access module to Phase 3 |

### 9.2 Risk Register

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Poor network coverage | High | High | Offline-first mobile app; USSD/SMS fallback | Mobile Engineers |
| Low farmer adoption | High | High | Train-the-trainer; incentives; local language support | Training Lead |
| API integration delays | Medium | Medium | Early engagement; mock APIs; parallel development | Backend Engineers |
| Security breach | Low | High | Encryption; RLS; regular security audits | QA & DevOps |
| Performance degradation | Medium | Medium | Load testing; horizontal scaling; monitoring | QA & DevOps |
| Hardware limitations | Medium | Medium | React Native + VS Code; physical device testing | All Engineers |
| Scope creep | High | Medium | Change control process; phased delivery | Project Director |
| Key team member departure | Low | High | Cross-training; documentation; code reviews | Project Director |

## 10. Quality Assurance Strategy

### 10.1 Testing Strategy

| Testing Level | Frequency | Owner | Tools |
| --- | --- | --- | --- |
| Unit Testing | Continuous (per commit) | All Engineers | Jest, Mocha |
| Integration Testing | Weekly | QA Engineer | Supertest, Postman |
| End-to-End Testing | Bi-weekly | QA Engineer | Playwright, Cypress |
| User Acceptance Testing | Per release | Training Lead + AFAP | Manual, User testing |
| Performance Testing | Monthly | QA Engineer | k6, JMeter |
| Security Testing | Quarterly | QA Engineer | OWASP ZAP, Burp Suite |

### 10.2 Code Quality Standards

| Standard | Implementation |
| --- | --- |
| Code Reviews | 100% of PRs reviewed by at least 1 peer |
| Linting | ESLint + Prettier (TypeScript) |
| Test Coverage | ≥ 80% (unit tests) |
| Branching Strategy | GitFlow (main → develop → feature) |
| CI/CD Pipeline | GitHub Actions (lint → test → build → deploy) |

## 11. Communication & Reporting

### 11.1 Meeting Cadence

| Meeting | Frequency | Attendees | Purpose |
| --- | --- | --- | --- |
| Daily Stand-up | Daily | Dev Team | Progress, blockers |
| Sprint Planning | Bi-weekly | Dev Team + PM | Sprint backlog |
| Sprint Review | Bi-weekly | Dev Team + PM + AFAP | Demo, feedback |
| Project Steering | Monthly | Project Director + AFAP PM | Status, risks, decisions |
| Quarterly Review | Quarterly | Project Director + AFAP PM + AFAP Exec | Strategic alignment |

### 11.2 Reporting

| Report | Frequency | Format | Recipient |
| --- | --- | --- | --- |
| Weekly Status Report | Weekly | PDF/Email | AFAP PM |
| Sprint Report | Bi-weekly | PDF | AFAP PM |
| Monthly Dashboard | Monthly | Live link + PDF | AFAP PM |
| Quarterly Progress Report | Quarterly | PDF | AFAP PM + Exec |
| Phase Completion Report | End of Phase | PDF | AFAP PM + Exec |

## 12. Success Metrics (End of 36 Months)

| Metric | Target | Measurement |
| --- | --- | --- |
| Farmers registered | ≥ 25,000 | Database count |
| Active farmers (≥1 transaction/month) | ≥ 70% | Platform analytics |
| CBAs trained and active | ≥ 150 | Training records |
| Agrodealers onboarded | ≥ 75 | Database count |
| Financial institutions integrated | ≥ 8 | Integration count |
| Off-takers integrated | ≥ 10 | Integration count |
| Credit applications processed | ≥ 1,000 | Database count |
| Input orders processed | ≥ 10,000 | Database count |
| Commodity sales via platform | ≥ 5,000 MT | Database count |
| Platform uptime | ≥ 99.5% | Monitoring |
| User satisfaction | ≥ 80% | Surveys |
| Reduction in manual reporting time | ≥ 50% | AFAP PM assessment |

## 13. Transition to Sustainability (Post-Contract)

### 13.1 Sustainability Strategy

| Area | Strategy |
| --- | --- |
| Technical | Full code ownership transferred to AFAP; documentation complete; DevOps tools handed over |
| Operational | AFAP staff trained to manage, maintain, and extend platform |
| Financial | Platform cost model designed for AFAP to sustain (SaaS hosting, support) |
| Community | CBAs and agrodealers self-sustaining as local champions |

### 13.2 Transition Deliverables (Months 33–36)

| Deliverable | Format | Owner |
| --- | --- | --- |
| Complete source code | GitHub repo | Project Director |
| DevOps and infrastructure documentation | Word/PDF | QA & DevOps |
| Platform administration manual | Word/PDF | Training Lead |
| Developer onboarding guide | Word/PDF | Training Lead |
| Data export and backup procedures | Word/PDF | QA & DevOps |
| Training completion certificates | Database records | Training Lead |
| Transition sign-off | PDF | Project Director + AFAP |

## 14. Appendices

### A. Detailed Gantt Chart (High-Level Timeline)

| Phase | Month 1-3 | 4-9 | 10-18 | 19-24 | 25-36 |
| --- | --- | --- | --- | --- | --- |
| Phase 1: Mobilisation | ████████ |  |  |  |  |
| Phase 2: Pilot |  | ████████████ |  |  |  |
| Phase 3: Scale-Up |  |  | ██████████████ |  |  |
| Phase 4: Optimisation |  |  |  | ████████████ |  |
| Phase 5: Support |  |  |  |  | ████████████████████ |

### B. Milestone Checklist

| Milestone | Phase | Completion Date |
| --- | --- | --- |
| Requirements sign-off | Phase 1 | [Date] |
| Platform MVP (Farmer Registration + USSD) | Phase 1 | [Date] |
| Pilot Launch | Phase 2 | [Date] |
| Mid-Pilot Review | Phase 2 | [Date] |
| Full Platform Launch (All Modules) | Phase 3 | [Date] |
| 15,000 Farmers Onboarded | Phase 3 | [Date] |
| Security Audit Complete | Phase 4 | [Date] |
| Mid-Term Review Complete | Phase 4 | [Date] |
| 25,000 Farmers Onboarded | Phase 5 | [Date] |
| Transition Plan Complete | Phase 5 | [Date] |
| Final Project Handover | Phase 5 | [Date] |

## 15. Document Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | [Date] | Kabelo | Initial draft |